## Sheet1
step | task | from | to | owner | completion
Concept | Groundwork | 2023-10-01 | 2023-10-05 | Cross teams | 1
Concept | MVP definition | 2023-10-06 | 2023-10-06 | Product | 1
Concept | Effort estimation | 2023-10-06 | 2023-10-09 | Cross teams | 1
Development | Back-end | 2023-10-12 | 2023-10-21 | Feature | 1
Development | Models training | 2023-10-19 | 2023-11-03 | Data science | 1
Development | User experience | 2023-10-12 | 2023-10-16 | UX | 1
Development | Front-end | 2023-10-19 | 2023-11-23 | Feature | 1
Development | Technical preview | 2023-10-28 | 2023-11-04 | Feature | 1
Productization | Code review | 2023-10-04 | 2023-11-06 | Feature | 1
Productization | Testing | 2023-11-05 | 2023-11-06 | Test | 1
Productization | Texts and documentation | 2023-11-02 | 2023-11-06 | Writers | 1
Productization | Beta release | 2023-11-09 | 2023-11-10 | Feature | 1
Release | Bug fixes | 2023-11-09 | 2023-11-13 | Feature | 1
Release | Final build | 2023-11-16 | 2023-11-17 | Cross teams | 0.75
Release | Deployment | 2023-11-11 | 2023-11-19 | DevOps | 0